## Daily Work Reports
Employee Name | Report Date | Reporting Manager | Project Name | Work Description | Blockers | Attachment | Review Status | Reviewed By | Review Comment | Submitted At | Reviewed At
Soham Kavde | 2026-07-01 | Shailesh Nagpure | smartudhar | 01-07-2026 Profile created Bug Fix Deploy code on live server | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:47 am | --
Soham Kavde | 2026-07-03 | Eiksha Upwanshi | smartudhar | 03-07-2026 Bug Fix Smart udhar par bug fix and structure development for subscription plan | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:48 am | --
Soham Kavde | 2026-07-06 | Eiksha Upwanshi | smartudhar | add on-off button for discription box (Default off for all product) change heading name in all transaction( monthly sale to All Transaction) Testing | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:48 am | --
Soham Kavde | 2026-07-07 | Shailesh Nagpure | smartudhar | 07-07-2026 reduce the memory size of invoice and quotation ex.26 kb,12 mb Show error massege properly it should take required numbers and word length should be correct meeting with mayank sir project update | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:49 am | --
Soham Kavde | 2026-07-08 | Shailesh Nagpure | smartudhar | Notification flow fix in backend and frontend Meeting with mayank sir Bug fix | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:51 am | --
Shubham Thakre | 2026-07-08 | Shailesh Nagpure | CRM Project | implementing biometric punchin out in CRM and attendance logics | -- | -- | PENDING | -- | -- | 20 Jul 2026, 11:03 am | --
Soham Kavde | 2026-07-09 | Shailesh Nagpure | smartudhar | Create All tab for both Website and App. Add Tax options: Inclusive and Exclusive (Fixed). Invoice optimisation report section Smart Score -1 to N/A | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:51 am | --
Shubham Thakre | 2026-07-09 | Shailesh Nagpure | CRM project | merging code with gouri and implementing leave logics in frontend. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 11:06 am | --
Soham Kavde | 2026-07-10 | Eiksha Upwanshi | smartudhar | total sum added in sell list,, All Transactions, Quotation List, Expense List, and Reports. statement download done | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:52 am | --
Shubham Thakre | 2026-07-10 | Shailesh Nagpure | CRM project | working on chat module. Implemented some features still working on it. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 11:09 am | --
Soham Kavde | 2026-07-13 | Shailesh Nagpure | smartudhar | otp channal added (sms or whatsapp) improved in smartudhar documents | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:53 am | --
Gouri Shankar | 2026-07-13 | Shailesh Nagpure | Office CRM | Notes Module add folder delete folder , rename folder api done Add note , edit note , pin note , add to favorite note api done. Share note , with permission of view , edit add to archive , move to trash , permanently delete folder and note api done Frontend Notes page developed and integration With sanjay Sir and Garima Ma’am meeting 2 3 hours | No | 1784012840276-483665946.jpeg | REVIEWED | Shubham Thakre | -- | 14 Jul 2026, 01:03 pm | 15 Jul 2026, 04:09 pm
Soham Kavde | 2026-07-14 | Shailesh Nagpure | smartudhar | Dashboard section | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:53 am | --
Shubham Thakre | 2026-07-14 | Shailesh Nagpure | CRM project | faced biometric issues, fixed them still examining the biometric logic. changed some features in chat and profile screens | -- | -- | PENDING | -- | -- | 20 Jul 2026, 11:10 am | --
Gouri Shankar | 2026-07-14 | Sirish Diyawar | CRM | 14-07-2026: With garimga ma’am all CRM employee side , Hr side every functiniolity explained. Cipera extended withdraw bug fixed . CRM emp dashboard leave amd daily task responsive fixed Live crm to backend and frontend on server so final touch of every api . and code | okk | -- | REVIEWED | Shubham Thakre | -- | 15 Jul 2026, 11:39 am | 15 Jul 2026, 04:08 pm
Soham Kavde | 2026-07-15 | Shailesh Nagpure | smartudhar | Dashboard section API Bug Fix, testing and meetings | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:53 am | --
Shubham Thakre | 2026-07-15 | Shailesh Nagpure | CRM project | faced error while pushing the CRM into production. fixed all the bugs. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 11:11 am | --
Shailesh Nagpure | 2026-07-15 | Yogesh Rangade | MM Bot | MM Bot - bifinance compatible bot creationtion , working on trade , chart , volume part office github copilot plan purchase prakratam domain renew office crm code live on server , and code upload 2 - 3 times | -- | -- | PENDING | -- | -- | 17 Jul 2026, 11:29 am | --
Amrita Mishra | 2026-07-15 | Sirish Diyawar | All projects | * CIPERA SOCIAL MEDIA CONTENT CREATION AND POSTING. * CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * UNDERSTANDING THE PAYMENT GATEWAY AND THERE PAYEMENT METHODS * PAYMENT GATEWAY SCRIPT AND VOICE OVER CREATION. | -- | -- | REVIEWED | Yogesh Rangade | -- | 17 Jul 2026, 10:26 am | 17 Jul 2026, 10:26 am
Swati Rinayat | 2026-07-15 | Sakshi Kawre | Intership Roadmap PPT | Our structured internship roadmap is designed to provide hands-on experience in UI/UX Design, Frontend Development, and Backend Development. Through practical projects, guided learning, and real-world assignments, interns gain the technical skills and confidence required to build industry-ready full-stack applications. | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 03:03 pm | 17 Jul 2026, 10:29 am
Gouri Shankar | 2026-07-15 | Shubham Thakre | CRM Backend | 15-07-2026: Crm Data Feed for all employees including their all details CRm server live problem bug debugging Chat module minor changes | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 12:33 pm | 17 Jul 2026, 10:29 am
Anshul Tiwari | 2026-07-15 | Gouri Shankar | CrypGPT | CrypGPT- post design | -- | -- | REVIEWED | Gouri Shankar | -- | 16 Jul 2026, 10:36 am | 16 Jul 2026, 01:46 pm
Aryant Shrirang | 2026-07-15 | Gouri Shankar | Payment gatway + dob website | payment gateway meeting with amrita maam , project code run env , logo fixes , video recording for marckating dob website , interns monitoring , website consistency check on there work , | UI misbehave due to new content | -- | REVIEWED | Gouri Shankar | -- | 16 Jul 2026, 10:24 am | 16 Jul 2026, 01:46 pm
Shivam Patle | 2026-07-15 | Eiksha | Smart Udhar | Worked on Smart Udhar application optimization. | -- | -- | REVIEWED | Yogesh Rangade | -- | 15 Jul 2026, 07:01 pm | 17 Jul 2026, 10:27 am
NUKUL Lilhare | 2026-07-15 | Eiksha | web3 development | Web3 development page created in figma. Task assign by (Aryant, Amman sir). | -- | -- | REVIEWED | Yogesh Rangade | -- | 15 Jul 2026, 06:55 pm | 17 Jul 2026, 10:27 am
Ashvin Bisen | 2026-07-15 | Eiksha | MLLF RWA | MLLF Website Homepage: Header, Hero & Invest Section develop Done. | -- | -- | REVIEWED | Yogesh Rangade | -- | 15 Jul 2026, 06:54 pm | 16 Jul 2026, 05:24 pm
Pankaj Nagpure | 2026-07-15 | Eiksha | DOB website SEO changes | Designed new web pages for the DOB website in Figma based on project requirements. Updated frontend code to align with the latest design. Improved page layout, UI consistency, responsiveness, and made necessary code modifications for better implementation and user experience | No major blockers. Minor changes are pending based on feedback and review | -- | REVIEWED | Yogesh Rangade | -- | 15 Jul 2026, 06:53 pm | 17 Jul 2026, 10:27 am
Sampann Tiwari | 2026-07-15 | Eiksha | Unihub | -Created the backend structure -Created the model for services, modules and users -Full backend integration for the Services and module -Integrated the APIs and Tested the working -Authentication flow created for the users -Login and Register Pages created -API integrated for the Login and Register -Full flow tested for the login, Register and Logout | -- | -- | REVIEWED | Yogesh Rangade | -- | 15 Jul 2026, 06:52 pm | 17 Jul 2026, 10:27 am
Nitu Bisen | 2026-07-15 | Eiksha | Stabixpay-website | Today, I worked on the StabixPay website frontend by improving its responsiveness across different screen sizes to ensure a seamless user experience on mobile, tablet, laptop, and desktop devices. I also implemented smooth UI animations to enhance the overall look and interactivity of the website. Additionally, I updated and refined several card components by adjusting their layout, spacing, alignment, and styling to better match the design requirements while maintaining consistency throughout the application. These improvements resulted in a more polished, responsive, and visually engaging user interface.and complete this website. | -- | -- | REVIEWED | Yogesh Rangade | -- | 15 Jul 2026, 06:50 pm | 17 Jul 2026, 10:27 am
Soham Kavde | 2026-07-16 | Eiksha Upwanshi | smartudhar | Testing full website bug fix mail option in collection section remove dynamic category name should be visible in dropdown image upload design not working in mobile all social media and app link added on home page check konsi email bani h support ke lie check list asc and desc | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:54 am | --
Shubham Thakre | 2026-07-16 | Shailesh Nagpure | CRM project | shared all the credentials with the employees and examining the CRm. found some bugs as well. fixed dashboard issues. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 11:12 am | --
Kalpit Gautam | 2026-07-16 | Sirish Diyawar | MLLF | MLLF PPT CONTENT SMARTUDHAR WEBSITE CONTENT | -- | -- | PENDING | -- | -- | 17 Jul 2026, 03:03 pm | --
Swati Rinayat | 2026-07-16 | Sakshi Kawre | MLLF Token development | designed the About Us page content, including company overview, mission, vision, core values, and team section. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 12:09 pm | --
Shubham Thakre | 2026-07-16 | Shailesh Nagpure | CRM Project | fixed build code for production. fixed bugs of CRM from PM/TL side. had meeting with yogesh sir | -- | -- | PENDING | -- | -- | 17 Jul 2026, 11:52 am | --
Dhurv Shukla | 2026-07-16 | Shubham Thakre | CLIENT LIST OF 2025 | Daily Calls and Meeting Format Date - 16/07/2026 - Thursday 1. New Call – 00 2. Old Database Call-20 3. Follow Call –2 4. Total Calls – 22. 5.Hot Clients - Qualified Calls – 0. Hot Clients – 1. Manoj Kumar Meena. 2. Shyam Verma. 3. Nilesh Baraskar. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 11:51 am | --
Sanjay Lilhare | 2026-07-16 | Shubham Thakre | Digital one box Smart udhar Accounting work | 1)punchin punch out data entry (ok) 2) Leave approval mail read (ok) 3) tool purchase mail read 4) shield 30% payment done check WhatsApp for shield update 5) handbook check krna hain design hui ya n hui Swati ma’am se Koi mistake to n h usme 6)check resume in mail (ok) Smart udhar Meeting Office CRM Meeting And Leave data Add | -- | -- | PENDING | -- | -- | 17 Jul 2026, 11:35 am | --
Shailesh Nagpure | 2026-07-16 | Yogesh Rangade | Multiple Project | office crm - code upload on server , server change , domain change multiple times aerux - backend problem fix equnix ai - backend code upload on server development team performance report create | -- | -- | PENDING | -- | -- | 17 Jul 2026, 11:28 am | --
Gouri Shankar | 2026-07-16 | Shubham Thakre | Office CRM | 16-07-2026: Worked on chat module . Participated on domain change server change . deployment bug fixes on server . Added tabs , in chat module with all , unread and separated group section . 2 hours Discussion on upcoming project module .+ logic explain to each emp related leave .. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 11:10 am | --
Sakshi Kawre | 2026-07-16 | Shubham Thakre | MLLF inner pages | Worked on the MLLF inner pages and completed the FAQ page design with consistent UI and responsive layout. Started designing the Contact Us page, focusing on layout structure, form design, and user-friendly interaction. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 10:52 am | --
Soham Kavde | 2026-07-16 | Shailesh Nagpure | smartudhar | Testing full website bug fix | -- | -- | PENDING | -- | -- | 17 Jul 2026, 10:46 am | --
Sakshi Kawre | 2026-07-16 | Shubham Thakre | Employee Performance report June | Prepared the performance report for team members, reviewing progress, task completion, and overall contributions. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 10:45 am | --
Amrita Mishra | 2026-07-16 | Shubham Thakre | All Projects | * CIPERA SOCIAL MEDIA CONTENT CREATION AND POSTING. * CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * CHANGES IN SCRIPT. * PAYMENT GATEWAY VIDEO CREATION * SALES AND MARKETING MEETING | -- | -- | REVIEWED | Yogesh Rangade | -- | 17 Jul 2026, 10:26 am | 17 Jul 2026, 10:30 am
Sampann Tiwari | 2026-07-16 | Shubham Thakre | Unihub | Unihub Backend for Inquiries created Inquiry model, controller and routes developed Integrated with the frontend form Contact form backend created Integrated the contact form API with frontend form Mail service created for inquiries after submission Tested the mail service User profile editing functionality created, integrated and tested Search bar issues fixed Improved the UI of login, registration and homepage Worked on the chatbot | AI integration code not available in the client's build | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 07:04 pm | 17 Jul 2026, 10:25 am
Nitu Bisen | 2026-07-16 | Yogesh Rangade | Mllf web and stabixpay | Today, I worked on the StabixPay website, where I implemented the feedback provided by my manager. I added smooth animations, improved the button layout, and made UI refinements to enhance the overall user experience. Additionally, I started working on the new MLLF Token project. I developed the Hero section based on the design and made it fully responsive across different screen sizes to ensure a consistent user experience on desktop, tablet, and mobile devices. | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 07:03 pm | 17 Jul 2026, 10:26 am
Ashvin Bisen | 2026-07-16 | Shailesh Nagpure | MLLF RWA | MLLF Website Homepage: Ecosystem, Property, real estate, prortfolio & Growing Section develop Done. | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 07:01 pm | 17 Jul 2026, 10:26 am
Pankaj Nagpure | 2026-07-16 | Shubham Thakre | DOB website updation | Created 5 new figma design for the DOB website and updated SEO-friendly content in the code.improved content structure and ensured consistency across pages Today, I worked on multiple website content and UI updates. I completed content changes on the Blockchain Development page, replaced the required section on the same page, removed unnecessary sentences from the Generative AI page, and updated its meta description for better SEO. Additionally, I fixed the missing card issue on the AI Development page. All assigned tasks were completed successfully and the requested updates have been implemented. | NO blockers | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 06:38 pm | 17 Jul 2026, 10:26 am
NUKUL Lilhare | 2026-07-16 | Shubham Thakre | Digital One Box | Web3 Marketing → Meta title, meta description, content replaced in Why Choose Digital One Box section Crypto Marketing → Meta title, meta description updated NFT Marketing → Meta title, meta description, card content fixed ICO‑IDO Marketing → Meta title, meta description updated, Why Choose Digital Box section completed NFT Services → Meta title, meta description updated NFT Marketplace Development → Meta title, meta description updated NFT Solution → Meta title, meta description updated, 3 cards added, canonical corrected ICO Services → Meta title, meta description updated, content refreshed IDO Services → Meta title, meta description updated, content refreshed SEO corrections and content additions completed across all listed pages. 4 pages designed in Figma for Digital One Box. | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 06:35 pm | 17 Jul 2026, 10:26 am
Anshul Tiwari | 2026-07-16 | Sirish Diyawar | Crypto logus | Crypto logus - post design | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 06:27 pm | 17 Jul 2026, 10:25 am
Anshul Tiwari | 2026-07-16 | Amrita Mishra | Finzo EX | finzoEX- web site graph chart image design | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 05:31 pm | 17 Jul 2026, 10:25 am
Anshul Tiwari | 2026-07-16 | Amrita Mishra | Silvernova | Silvernova - post design | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 05:31 pm | 17 Jul 2026, 10:25 am
Anshul Tiwari | 2026-07-16 | Amrita Mishra | CrypGPT | CrypGPT - post & animated GIF video design | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 05:30 pm | 17 Jul 2026, 10:25 am
Anshul Tiwari | 2026-07-16 | Amrita Mishra | Cipera | Cipera - long reel design & reel cover image design | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 05:30 pm | 17 Jul 2026, 10:30 am
Amaan Khan | 2026-07-16 | Sirish Diyawar | Digital One Box Webpage SEO | Webpage Digital one Box -: 1. Content Optimization 2. Keyword research for New page 3. Creating FAQ's For the pages 4. AEO and GEO Optimization for pages. 5. Review all the Updated content of DOB webpages 6. Finding issues and give it for correction New Webpages content Created :- 1. Cryptocurrency Exchange Development 2. Trading Bot Development 3. Security Token Development 4. Utility Token Development 5. Governance Token Development 6. Real Estate Tokenization 7. ICO Token Development 8. NFT Launchpad Development 9. NFT Wallet Development 10. NFT Staking Platform 11. NFT Exchange Development 12. NFT Marketplace White Label Document link - https://docs.google.com/document/d/11842yeJjZEar42fvAoXxsTyqPX61uKnbOKJ1Lyz0VuI/edit?usp=sharing | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 04:44 pm | 17 Jul 2026, 10:29 am
Priyank Khairwar | 2026-07-16 | Shubham Thakre | ORAXEL,FINZO EX | ORAXEL Landing Page Wireframe completed FINZO EX Inner page (login \signup) | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 11:00 am | 17 Jul 2026, 10:29 am
Amaan Khan | 2026-07-16 | Shubham Thakre | Webpage Addon Work | "Webpage Digital one Box -: 1. Content Optimization 2. Keyword research for New page 3. Creating FAQ's For the page 4. AEO and GEO Optimization for page. Webpages:- 1. dAPP Development 2. StableCoin development 3. Multi-Currency Wallet Development 4. Crypto Payment Gateway" | -- | -- | REVIEWED | Yogesh Rangade | -- | 16 Jul 2026, 10:56 am | 16 Jul 2026, 05:23 pm
Anshul Tiwari | 2026-07-17 | Amrita Mishra | Cipera | Cipera - post design And meme post design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:31 pm | --
Anshul Tiwari | 2026-07-17 | Eiksha Upwanshi | CrypGPT | CRypGPT - post design and meme post design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:30 pm | --
Anshul Tiwari | 2026-07-17 | Eiksha Upwanshi | Silvernova | Silvernova - post design and meme post design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:30 pm | --
Soham Kavde | 2026-07-17 | Shailesh Nagpure | smartudhar | Code deploy in VPS new screen develop : payment screen worked on backend for purchase section | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:56 am | --
Amrita Mishra | 2026-07-17 | Sirish Diyawar | All project | 17-07-2026 * 2 DAYS CIPERA SOCIAL MEDIA CONTENT CREATION AND POSTING. * 2 DAYS CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * 2 DAYS SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * PAYMENT GATEWAY VIDEO COMPLETE. * ONE MONTH NEW LEARNING REPORT CREATION FOR SATURDAY MEETING. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 01:01 pm | --
Shubham Thakre | 2026-07-17 | Shailesh Nagpure | CRM project | pushed latest code in production. had meeting regarding project management with yogesh sir. Module 1 is finished. but still examining the CRM to avoid data issues. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 11:14 am | --
Amrita Mishra | 2026-07-17 | Sirish Diyawar | ALL PROJECT | * 2 DAYS CIPERA SOCIAL MEDIA CONTENT CREATION AND POSTING. * 2 DAYS CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * 2 DAYS SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * PAYMENT GATEWAY VIDEO COMPLETE. * ONE MONTH NEW LEARNING REPORT CREATION FOR SATURDAY MEETING. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 10:29 am | --
Shailesh Nagpure | 2026-07-17 | Yogesh Rangade | mm bot | MM Bot - bifinance compatible bot creationtion , working on trade , chart , volume part | -- | -- | PENDING | -- | -- | 20 Jul 2026, 10:27 am | --
Swati Rinayat | 2026-07-17 | Sakshi Kawre | MLLF token development | Created the MLLF Token landing page featuring token details, utility features, real estate tokenization, staking, governance, rewards, and responsive UI components. | -- | -- | PENDING | -- | -- | 18 Jul 2026, 10:49 am | --
Aryant Shrirang | 2026-07-17 | Shubham Thakre | DOB website | Dob website ui , updation for letest incomming pages , | -- | -- | PENDING | -- | -- | 18 Jul 2026, 10:38 am | --
Shivam Patle | 2026-07-17 | Shubham Thakre | Smart Udhar | 1. Fixed the notification count issue in the top navigation. 2. Worked on translator integration and related improvements. 3. Added redirection (eye/arrow icon) in Collection, Purchase, and Sales modules. 4. Updated the Expense module by replacing Notes with Item Name. 5. Improved Product module functionality, including debouncing and import/export. 6. Performed validation and checks for invoice-related functionality. 7. Updated Smart Score color logic based on defined score ranges. 8. Fixed Sale List calculations for Total Paid, Total Amount, and Pending Amount. 9. Worked on Expense filter functionality to match the website. 10. Updated the main navigation sequence to align with the website. 11. Improved the All Transactions screen to match the website design and functionality. 12. Worked on the Payment Reminder section under Notifications. 13. Updated the Settings module to match the website. 14. Fixed multiple Legal Notice module issues, including keyboard behavior, owner name display, invoice API integration, preview data, invoice date, submit flow, price display after sharing, and input alignment. 15. Performed testing and verification of all implemented fixes and improvements. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 07:15 pm | --
Ashvin Bisen | 2026-07-17 | Shailesh Nagpure | MLLF RWA | MLLF Website Homepage: Future, Footer Section & Business page : hero & Property section develop Done. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 07:10 pm | --
Gouri Shankar | 2026-07-17 | Shailesh Nagpure | CRM Backend | holiday module frontend issue fixed . chadule module mobile responsive. drag and drop photos doc feature added . attendance some minor changes Dashboard timer and info for mobile fixed | -- | -- | PENDING | -- | -- | 17 Jul 2026, 07:08 pm | --
Sampann Tiwari | 2026-07-17 | Shubham Thakre | Unihub | Unihub Chatbot structure studied Integrated into the Base44's code Created the backend for the Chatbot Chatbot Ui created Chat bot tested Integrated the API into the frontend Changed the home page UI announcement modal image changed Made the changes told by the client Admin panel created Dashboard, Inquiry and User pages created Developed the admin backend Integrated the Admin frontend and backend | -- | -- | PENDING | -- | -- | 17 Jul 2026, 07:04 pm | --
Nitu Bisen | 2026-07-17 | Shailesh Nagpure | mllf-web | Today, I worked on the MLLF website. I developed three sections/pages of the Home page based on the provided design. I focused on implementing a responsive layout, ensuring the UI works smoothly across desktop, tablet, and mobile devices while maintaining design consistency. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 06:59 pm | --
Akshay Daharwal | 2026-07-17 | Yogesh Rangade | DevOps work (Unihub and CRM) | * Configured proxy setup for the UNIHUB project on the new IP address and domain. * Deployed the UNIHUB Frontend and Backend on the production server. * Set up the new CRM project environment on the server. * Deployed the CRM Frontend and Backend on the production server. * Resolved newly identified bugs in both projects and deployed the fixes to the live server. * Verified deployment, server configuration, and application functionality after production release. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 06:58 pm | --
Yogesh Rangade | 2026-07-17 | Shubham Thakre | Project Management | Project Management - Team Management - Client Management - Task Management - DOB Maintenance Policy Creation - TL Monthly Work Report Creation And Analysis MLLF Project Update Client Meeting Inhouse Project Deadline Report Creation. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 06:57 pm | --
Dhurv Shukla | 2026-07-17 | Shubham Thakre | CLIENT LIST OF 2025 | Daily Calls and Meeting Format Date - 17/07/2026 - Thursday 1. New Call – 00 2. Old Database Call-53 3. Follow Call –7 4. Total Calls –60 5.Hot Clients - Qualified Calls – 0. Hot Clients – 3 1. Arvind Kumar Singh 2. Manish Dahiya 3. Chokharam Chokharam Godara.. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 06:57 pm | --
NUKUL Lilhare | 2026-07-17 | Shubham Thakre | DOB figma design , code fix | ✅ Work Completed Fixed code issues on the DOB website to improve stability and functionality. Applied corrections as per the rework sheet for smoother user experience. Designed and refined Figma layouts for DOB, ensuring consistency with the updated website flow. 🎯 Outcome Website errors resolved, improving reliability. Figma design aligned with project requirements, ready for review and integration. 🔜 Next Steps Continue testing website modules for hidden bugs. Finalize Figma prototype and share with the team for feedback. | -- | -- | PENDING | -- | -- | 17 Jul 2026, 06:45 pm | --
Pankaj Nagpure | 2026-07-17 | Shubham Thakre | Digital One Box Website updation | Designed three website pages in Figma based on SEO-friendly content requirements. Updated the Figma designs according to the finalized SEO content and layout improvements. Made minor changes to the website code to match the latest design updates. Cross-verified the implemented code with the Figma designs to ensure consistency. Identified and fixed minor code bugs to improve functionality and UI accuracy. | No blockers. All assigned tasks were completed successfully. | -- | PENDING | -- | -- | 17 Jul 2026, 06:45 pm | --
Amaan Khan | 2026-07-17 | Sirish Diyawar | Digital One Box SEO | Content Review & Team Feedback Reviewed the updated content across assigned sections. Identified areas requiring improvement and provided rework instructions to the team to ensure quality and consistency. Digital One Box Website Review Collaborated with Aryant Sir to review the Digital One Box website. Inspected webpages for visual errors, UI inconsistencies, layout issues, and other website-related problems. Documented the identified issues and reported them to Aryant Sir for necessary fixes and improvements. SEO & Service Page Meeting Attended a meeting with Yogesh Sir to discuss ongoing SEO work and the implementation of new service page additions. Team Meeting Attended the team meeting with Sirish Sir. Provided updates on my ongoing work, discussed team performance, and shared progress on assigned tasks. | -- | -- | REVIEWED | Sirish Diyawar | -- | 17 Jul 2026, 06:27 pm | 17 Jul 2026, 06:54 pm
TESTING EMPLOYEE | 2026-07-17 | Shubham Thakre | tesing work | something is comingss | -- | -- | REVIEWED | Testing Bot | -- | 17 Jul 2026, 03:22 pm | 17 Jul 2026, 03:33 pm
Aryant Shrirang | 2026-07-17 | Testing Bot | DOB new website + AI agent meeting | dob wesite , reconfiguration design , and responsive for laptop and tablet , AI product meeting | -- | -- | PENDING | -- | -- | 17 Jul 2026, 09:57 am | --
Soham Kavde | 2026-07-18 | Shailesh Nagpure | smartudhar | Subscription plan api development. flow creation Frontend UI Development, API integration | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:56 am | --
Swati Rinayat | 2026-07-20 | Sakshi Kawre | MLLF RWA Token development | Designed the MLLF Business Plan page, including strategy overview, business model, token value generation, growth strategy and governance sections. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:29 am | --
Sakshi Kawre | 2026-07-20 | Eiksha Upwanshi | MLLF Project | Finalized the MLLF Presale page, completing the UI design, layout refinements, and final visual enhancements. Explored projects on CoinSniper and CoinMarketCap for market research, feature analysis, and design inspiration. | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:47 pm | --
Amrita Mishra | 2026-07-20 | Eiksha Upwanshi | All project | * CIPERA SOCIAL MEDIA CONTENT CREATION. * REEL CREATION AND POSTING. * CRYPGPT SOCIAL MEDIA CONTENT CREATION. * GRAPHIC CREATION AND POSTING. * SRN SOCIAL MEDIA CONTENT CREATION. * GRAPHIC CREATION AND POSTING. * ELITE X MINING CONTENT CREATION. * GRAPHIC CREATION AND POSTING. * FUND ADD-ON DOB CAMPAIGN AND CAMPAIGN OPTIMIZATION. * AI AGENT CHAT BOT TESTING | -- | -- | PENDING | -- | -- | 22 Jul 2026, 10:25 am | --
Sirish Diyawar | 2026-07-20 | Yogesh Rangade | Daily Task 20-07-26 | Daily Task 20-07-26 20-07-2026 Working on Whatsapp Automation 20-07-2026 Meeting with marketiong team 20-07-2026 meeting with samrt udhar team | -- | -- | PENDING | -- | -- | 21 Jul 2026, 06:53 pm | --
Dhurv Shukla | 2026-07-20 | Eiksha Upwanshi | CLIENT LIST 2025 | Daily Calls and Meeting Format Date - 20/07/2026 - Monday 1. New Call – 00 2. Old Database Call-38 3. Follow Call –7 4. Total Calls –45 5.Hot Clients - Qualified Calls – 0. Hot Clients – 0 | -- | -- | PENDING | -- | -- | 21 Jul 2026, 05:42 pm | --
Shubham Thakre | 2026-07-20 | Shailesh Nagpure | CRM project | Had meeting with yogesh sir regarding project management. | -- | -- | PENDING | -- | -- | 21 Jul 2026, 11:01 am | --
Soham Kavde | 2026-07-20 | Shailesh Nagpure | smartudhar | Subscription plan second half meeting with SmartUdhar complete team | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:57 am | --
Ashvin Bisen | 2026-07-20 | Shailesh Nagpure | MLLF RWA | MLLF Website FAQS Page , About Page : Hero Section , presale page hero & buy Now Section & Bussniss page : How MLLF, The Ecosystem, CTA & HOW WE SCALE section develop Done. | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:52 am | --
Nitu Bisen | 2026-07-20 | Eiksha Upwanshi | Mllf-web | Today, I continued development of the MLLF Web project and completed a significant portion of the landing page. Developed three responsive sections of the landing page based on the Figma design. Implemented clean, reusable React components with Tailwind CSS for consistent styling. Ensured the newly built sections are fully responsive across desktop, tablet, and mobile devices. Added proper spacing, typography, layouts, and UI elements to closely match the design specifications. Started working on the second page of the website. Built two sections for the second page, maintaining the same design system and responsive behavior. Focused on component structure, code reusability, and pixel-perfect implementation while keeping the UI optimized for different screen sizes. | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:44 am | --
Aryant Shrirang | 2026-07-20 | Eiksha Upwanshi | DOB website + AI calling agent dashboad work | DOB website content ui monitoring , guided team what to do , resolve bugs and tought them about git use Ai calling agent meeting with provider, calling agent dashboard view perfection , mobilenumber attac and detach option , to ai agent | provider , schedule meeting at night 8 pm | -- | PENDING | -- | -- | 21 Jul 2026, 10:28 am | --
Shailesh Nagpure | 2026-07-20 | Yogesh Rangade | MM Bot | MM Bot - bifinance compatible bot creationtion , working on trade , chart , volume part genvault - price change and code upload on server blockbuster - backend errof fix and minor correction and code upload on server , client demo Ashiv - review meeting done | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:25 am | --
Kalpit Gautam | 2026-07-20 | Eiksha Upwanshi | smart udhar | working on website content | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:19 am | --
Gouri Shankar | 2026-07-20 | Yogesh Rangade | CRM Backend | 20-07-2026: Chat module mobile responsive with search and whtsapp style interface for conversation Meeting with yogesh Sir + Shubham Sir for project module Information gathering on project module + flow analysis Ticket module Foundation . | -- | -- | PENDING | -- | -- | 21 Jul 2026, 10:19 am | --
Akshay Daharwal | 2026-07-20 | Yogesh Rangade | FinzoX and Elite X | * Performed API testing for the Finzo X project. * Developed a new $10 registration API for the Elite X project. * Created a GET API to fetch registration details. * Integrated the APIs with the frontend and verified the functionality. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 07:10 pm | --
Amaan Khan | 2026-07-20 | Sirish Diyawar | Digital One Box SEO | Digital One Box Website Review:- a.) Review the Digital One Box website. b.) Inspected webpages for visual errors, UI inconsistencies, layout issues, and other website-related problems. c.) Documented the identified issues and reported them to developers for necessary fixes and improvements. Webpage Digital one Box -: 1. Content Optimization 2. Keyword research for New page 3. Creating FAQ's For the pages 4. AEO and GEO Optimization for pages. 5. Create Robot.txt for website New Webpages content Created :- 1. AI Agent Development 2. AI + Web3 Solutions" | -- | -- | PENDING | -- | -- | 20 Jul 2026, 07:07 pm | --
Shivam Patle | 2026-07-20 | Eiksha Upwanshi | Smart Udhar | Attended a meeting with Soham Sir to discuss project updates and implementation priorities. Participated in a discussion with Ashirwad Sir and Mayank Sir regarding the required application changes. Reviewed and finalized the list of enhancement points discussed during the meetings. Implemented the changes and improvements based on the agreed requirements. Updated the application according to the discussed business and UI/UX requirements. Tested and verified all implemented changes to ensure they were working as expected. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 07:05 pm | --
Sanjay Lilhare | 2026-07-20 | Eiksha Upwanshi | Digital one box and smart udhar | Day 20.07.2026 1)punchin punch out data entry (ok) 2) Leave approval mail read (ok) 3) tool purchase mail read Office CRM Meeting And Leave data Add meeting Form 16 Create Office stationery purchase Pending Payment Remainder | -- | -- | PENDING | -- | -- | 20 Jul 2026, 07:04 pm | --
Pankaj Nagpure | 2026-07-20 | Eiksha Upwanshi | Digital One Box Website | Updated images on the newly designed Figma pages. Fixed bugs on the existing website pages to improve functionality and UI consistency. Added new website pages based on the latest project requirements. Cross-verified the content on all newly added pages to ensure accuracy and consistency with the provided content. Performed overall quality checks to ensure the website updates were implemented correctly. | No blockers. All assigned tasks were completed successfully. | -- | PENDING | -- | -- | 20 Jul 2026, 07:04 pm | --
Sampann Tiwari | 2026-07-20 | Eiksha Upwanshi | FinzoEx, Genvault | Genvault Updated the Presale Page Changed the timer duration for seed round added the price announcement for seed round Finzoex Started the development of the home page Hero section developed Navbar developed Responsive design check for hero section Checked the responsive design of the Navbar Other sections basic structure ready | -- | -- | PENDING | -- | -- | 20 Jul 2026, 07:04 pm | --
Sakshi Kawre | 2026-07-20 | Eiksha Upwanshi | MLLF PRESALE | Finalized the MLLF Presale page, completing the UI design, layout refinements, and final visual enhancements. | -- | -- | PENDING | -- | -- | 20 Jul 2026, 07:00 pm | --
Nukul Lilhare | 2026-07-20 | Shailesh Nagpure | Dob figma design and code fix | make 2 page of figma and replace image also fix some code of Dob . | -- | -- | PENDING | -- | -- | 20 Jul 2026, 06:50 pm | --
Kalpit Gautam | 2026-07-20 | Sirish Diyawar | GENVAULT | GENVALUT TOKENOMICS UPDATE , MEETING WITH GENVALUT CLIENT , MLLF PPT CONTENT | -- | -- | PENDING | -- | -- | 20 Jul 2026, 01:50 pm | --
Priyank Khairwar | 2026-07-20 | Eiksha Upwanshi | FINZO EX | FINZO EX : KYC screens . | -- | -- | PENDING | -- | -- | 20 Jul 2026, 10:23 am | --
Shailesh Nagpure | 2026-07-21 | Yogesh Rangade | MM Bot | genvualt - error check MM Bot - bifinance compatible bot creationtion , working on trade , chart , volume part | -- | -- | PENDING | -- | -- | 27 Jul 2026, 12:25 pm | --
Soham Kavde | 2026-07-21 | Shailesh Nagpure | smartudhar | admin side plan purchase section | -- | -- | PENDING | -- | -- | 24 Jul 2026, 10:52 am | --
Swati Rinayat | 2026-07-21 | Sakshi Kawre | PPT OF MLLF | MLLF PPT ( i worked main slide, about us section, why MLLF, mission $ vission, ecossytem, key benefits, investment packages, packages highlights, and referral income system and their benefits) | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:33 am | --
Aryant Shrirang | 2026-07-21 | Yogesh Rangade | Ai calling agent | Ai calling agent new features added edit agent + delete agent , edit about system prompt and all other schduling perametor call ending condition meeting with mayank sir , 1 hr meeting with sirish sir | meeting with mayank sir + sirish sir | -- | PENDING | -- | -- | 22 Jul 2026, 05:47 pm | --
Shubham Thakre | 2026-07-21 | Shailesh Nagpure | CRM Project | 1. we are implementing initial modal of project management 2. PWA of our CRM is done. i'm fixing the paths for images and icons in PWA configuration. you'll get this version today. meanwhile, gouri fixed chat module for PWA. 3. SMTP integration also completed for leave module. All high authorities members will get a copy of leave application in gmail and notification in CRM with all status. | -- | -- | PENDING | -- | -- | 22 Jul 2026, 01:14 pm | --
Sakshi Kawre | 2026-07-21 | Eiksha Upwanshi | learning and exploring | Explored and researched modern UI/UX design trends for inspiration and best practices. Started learning Adobe Photoshop, focusing on essential tools, image editing, and design techniques. | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:56 pm | --
Anshul Tiwari | 2026-07-21 | Amrita Mishra | CrypGPT | CrypGPT - post design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:28 pm | --
Anshul Tiwari | 2026-07-21 | Eiksha Upwanshi | Cipera | Cipera - post design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:27 pm | --
Anshul Tiwari | 2026-07-21 | Amrita Mishra | Silvernova | Silvernova - post design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:27 pm | --
Anshul Tiwari | 2026-07-21 | Sirish Diyawar | Digital one box | Digital one box - reel design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:26 pm | --
Ashvin Bisen | 2026-07-21 | Shailesh Nagpure | MLLF | MLLF Website Token Page: Hero Section , About Page All Sections , presale page All Sections develop Done. | -- | -- | PENDING | -- | -- | 22 Jul 2026, 10:44 am | --
Nitu Bisen | 2026-07-21 | Shailesh Nagpure | mllf-web | Today, I continued developing the MLLF web application by implementing multiple pages and sections based on the project design. Work Completed FAQ Page Development Built the complete FAQ page layout. Developed all required FAQ sections with a clean and user-friendly structure. Ensured the design matches the provided UI and maintains consistency across the website. About Page Development Created the About page. Implemented two key sections with responsive layouts. Focused on proper content alignment, spacing, typography, and reusable React components. Readpaper Page Developed the final section of the Readpaper page. Integrated the section into the existing page structure while maintaining consistent styling and responsiveness. | -- | -- | PENDING | -- | -- | 22 Jul 2026, 10:03 am | --
Sanjay Lilhare | 2026-07-21 | Eiksha Upwanshi | Digital One Box PVT LTD And Smart Udhar PVT LTD | Daily Balance sheet Update Project management sheet Update Cilling fan Instaling Permision Process Pending Payment Remainder Smart Udhar Meeting Office Mobile Number Recharge Form 16 Create | -- | -- | PENDING | -- | -- | 21 Jul 2026, 07:07 pm | --
Sampann Tiwari | 2026-07-21 | Eiksha Upwanshi | FinzoEX | Hero section completed Added images to the hero section Applied animation to the Hero section Responsive behaviour fixed Navbar design completed Mobile Navbar created Navbar responsive design tested Ticker section fixed Stats section fixed | -- | -- | PENDING | -- | -- | 21 Jul 2026, 07:05 pm | --
Akshay Daharwal | 2026-07-21 | Yogesh Rangade | EliteX and Finzo X | * Created the Admin Registration Fee Get API for the Elite X project. * Developed and integrated the Admin Panel UI for Elite X. * Fixed User-side API bugs and ensured proper functionality. * Performed FinzoX API testing and completed the Frontend setup. | -- | -- | PENDING | -- | -- | 21 Jul 2026, 07:01 pm | --
Nukul Lilhare | 2026-07-21 | Shailesh Nagpure | Figma design of Dob | Design two template of Dob page , and replace all image in previous figma design. | -- | -- | PENDING | -- | -- | 21 Jul 2026, 06:59 pm | --
Pankaj Nagpure | 2026-07-21 | Shailesh Nagpure | DOB website | Designed 2 new SEO-friendly website pages for the Digital One Box website in Figma. Improved the alignment and layout of existing website pages using CSS. Updated new images in the Figma designs to enhance the visual appearance. Ensured the new page designs followed the existing design system and branding guidelines. Cross-verified the updated designs and UI changes for consistency and responsiveness. | NO | -- | REVIEWED | Shubham Thakre | -- | 21 Jul 2026, 06:55 pm | 27 Jul 2026, 12:03 pm
Sirish Diyawar | 2026-07-21 | Yogesh Rangade | Daily Task 21-07-26 | 21-07-2026 Crypto Logus social media content creation and posting. 21-07-2026 DOb reel Posting 21-07-2026 Working on Whatsapp Automation 21-07-2026 Core team meeting 21-07-2026 Interview Meeting Of data analyst | -- | -- | PENDING | -- | -- | 21 Jul 2026, 06:54 pm | --
Gouri Shankar | 2026-07-21 | Shailesh Nagpure | Office CRM | 21-07-2026: Project module Discusioon overall info gathering +meeting Smtp initialization + node mailer setup + Code merge + runtime Notification On leave module attached gmail facility , in app notification , Approve , Reject , Pending all 4 Desgined developed from backend to frontend . Ticket Module Real life info gathering | -- | Screenshot_22.png | PENDING | -- | -- | 21 Jul 2026, 06:53 pm | --
Amaan Khan | 2026-07-21 | Sirish Diyawar | Digital One Box SEO | " Digital One Box Website Review Review the Digital One Box website. Inspected webpages for visual errors, UI inconsistencies, layout issues, and other website-related problems. Resolve the content Issues with Developer Webpage Digital one Box -: 1. Content Optimization 2. Keyword research for New page 3. Creating FAQ's For the pages 4. AEO and GEO Optimization for pages. New Webpages content Created :- 1. AI Blockchain Integration 2. AI Chatbot Development 3. AI-powered DApps" | -- | -- | PENDING | -- | -- | 21 Jul 2026, 06:49 pm | --
Dhurv Shukla | 2026-07-21 | Eiksha Upwanshi | CLIENT LIST OF 2025 | Daily Calls and Meeting Format Date - 21/07/2026 - Monday 1. New Call – 00 2. Old Database Call-37 3. Follow Call –12 4. Total Calls –49 5.Hot Clients - Sanjay Powale – Company ka portfolio bhej diya hai client btayege unki requirement ka hai krke. Mukesh Kumar Yadav - Company Portfolio and Demo diye hai for token development. Enayat Khan – Interested hai token development me but 50% knowledge hai market ka Doges (DOGESH) - Token Development. Aman Jain – Memes Coin Banana Hai. Suklal Mahato – Kal call krke confirm karenge. Bipin Parida - Kal call krke confirm karenge. Rajiv - Kal call krke confirm karenge. Vikash Khushwaha – Aaj Call krne bole hai 7 bje ke baad regarding token development. Qualified Calls – RAJU (PRASANNATH K) - TOKEN DEVELOPMENT. | -- | -- | PENDING | -- | -- | 21 Jul 2026, 09:53 am | --
Shailesh Nagpure | 2026-07-22 | Yogesh Rangade | MM Bot - | aws equinix project - db clone for development ( aryant required ) MLLF -presale intregation part done , code upload on server , client demo MM Bot - bifinance compatible bot creationtion , working on trade , chart , volume part | -- | -- | PENDING | -- | -- | 27 Jul 2026, 12:25 pm | --
Soham Kavde | 2026-07-22 | Shailesh Nagpure | smartudhar | user side api integration in subscription plan, api integeration meeting with sirish sir | -- | -- | PENDING | -- | -- | 24 Jul 2026, 11:12 am | --
Sakshi Kawre | 2026-07-22 | Eiksha Upwanshi | MLLF RWA Project | Implemented design updates in the MLLF project by adding the Tokenomics section, Contract Address section, and making UI/content enhancements across multiple pages. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 11:03 am | --
Aryant Shrirang | 2026-07-22 | Eiksha Upwanshi | Equinix AI + crypto logus + dob website | equinix ai new changes by client , cryptologus changes and updation , dob site monitoring and consistency guidance | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:47 am | --
Swati Rinayat | 2026-07-22 | Eiksha Upwanshi | PPT OF MLLF | i worked on remaining slides including multi level income system, distribution model, profit structure, rank & reward, token allocation and closing statement | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:35 am | --
Anshul Tiwari | 2026-07-22 | Eiksha Upwanshi | CIPERA | CIPERA - ai long video design and Reel cover image | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:27 am | --
Anshul Tiwari | 2026-07-22 | Amrita Mishra | CrypGPT | CrypGPT - post design | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:27 am | --
Anshul Tiwari | 2026-07-22 | Eiksha Upwanshi | Silvernova | Silvernova - post design | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:26 am | --
Anshul Tiwari | 2026-07-22 | Sirish Diyawar | UNIHUB | UNIHUB - logo design | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:26 am | --
Shubham Thakre | 2026-07-22 | Shailesh Nagpure | CRM project | Discussed about the flow of project management and started working on it. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:26 am | --
Ashvin Bisen | 2026-07-22 | Shailesh Nagpure | MLLF | MLLF Website Token Page All Sections, Contact page Develop , Term & Condition Page Develop & Privacy policy Page Develop & Home Page Tokenomics, Contract Address Section develop & Faqs Page Content Update Done. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 10:39 am | --
Amrita Mishra | 2026-07-22 | Sirish Diyawar | ALL TASK | 22-07-2026 * CIPERA SOCIAL MEDIA CONTENT CREATION AND POSTING. * CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * ELITE X MINING CONTENT AND GRAPHIC CREATION AND POSTING. * LEADS DATA ANALYSIS LAST WEEK REPORT CREATION, MISSING POINT READY FOR SALES TEAM. * AI AGENT TESTING * MEETING WITH SALES TEAM. * MEETING WITH TL | -- | -- | PENDING | -- | -- | 23 Jul 2026, 10:25 am | --
Amaan Khan | 2026-07-22 | Sirish Diyawar | Digital One Box SEO | " Digital One Box Webpage Review Review the Digital One Box New Webpages Figma Template Inspected pages for layout issues, and alignments Guide Interns For layout and format setting on figma Webpage Digital one Box -: 1. Content Research 2. Keyword research for New page 3. Creating FAQ's For the pages 4. AEO and GEO Optimization for pages. Cryptologus project:- 1. Topic research and keyword mapping 2. Write blog for cryptologus 3. generate Images for blog New Webpages content Created :- 1. AI Trading Bot Development 2. AI Workflow Automation 3. Custom Blockchain Development 4. Blockchain Explorer Development 5. Public Blockchain Development 6. Layer 1 Blockchain Development 7. Layer 2 Blockchain Development 8. DAO Development" | -- | -- | PENDING | -- | -- | 23 Jul 2026, 10:12 am | --
Nitu Bisen | 2026-07-22 | Shailesh Nagpure | mllf-web | Today, I continued development of the MLLF Web project by working on several key website sections. I focused on building the About, Tokenomics, Contact Us, and Presale page sections using React.js, Tailwind CSS, and Vite. Tasks Completed Developed the initial structure and layout for the About section. Built the Tokenomics section based on the provided Figma design. Started implementing the Contact Us section with responsive layout and styling. Developed the initial UI for the Presale page and organized its component structure. Applied responsive design techniques to ensure compatibility across desktop, tablet, and mobile devices. Maintained reusable React components and consistent styling using Tailwind CSS. Current Status The above sections have been partially completed and are currently under development. Some UI refinements, responsiveness adjustments, animations, and final content integration are still pending. The remaining work will focus on achieving pixel-perfect Figma implementation and completing functionality. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 10:04 am | --
Gouri Shankar | 2026-07-22 | Eiksha Upwanshi | Office - CRM Backend | 22-07-2026: Office Crm project module meeting and final flow for what we are going to develop . PM create project with all required field , list of all project , Api Developed Initial setup done for project module with all active project , Search all project and with project search ID done | -- | Screenshot_25.png | PENDING | -- | -- | 22 Jul 2026, 07:14 pm | --
Sanjay Lilhare | 2026-07-22 | Eiksha Upwanshi | Digital One Box | Pending Payment Reminder Daily Balance sheet Update Project management sheet Update Market visit MMSKY Registration on company MMSKY meeting oddo account meeting | -- | -- | PENDING | -- | -- | 22 Jul 2026, 07:02 pm | --
Dhurv Shukla | 2026-07-22 | Eiksha Upwanshi | FOLLOW UP CALLS IN CLIENT LIST 2025 | Daily Calls and Meeting Format Date - 22/07/2026 - Wednesday 1. New Call – 00. 2. Old Database Call- 05. 3. Follow Call – 27. 4. Total Calls –32. Qualified Calls – 00. | -- | -- | PENDING | -- | -- | 22 Jul 2026, 07:01 pm | --
Akshay Daharwal | 2026-07-22 | Yogesh Rangade | Finzoex and CRM Project | Yeh points professional English me: * Resolved backend connectivity issues in the Finzoex project. * Performed comprehensive API testing and fixed multiple API-related bugs. * Deployed the CRM Frontend code to the live server. * Deployed the CRM Backend code to the live server. | -- | -- | PENDING | -- | -- | 22 Jul 2026, 06:57 pm | --
Nukul Lilhare | 2026-07-22 | Shailesh Nagpure | Dob Figma design | Updated website content for the Digital One Box (DOB) webpage in Figma. Replaced existing content with new, SEO-friendly copy. Updated images and visual assets to match the new branding and services. Redesigned the Figma layout while maintaining a clean, modern UI/UX. | -- | -- | REVIEWED | Shubham Thakre | -- | 22 Jul 2026, 06:56 pm | 27 Jul 2026, 12:06 pm
Pankaj Nagpure | 2026-07-22 | Shailesh Nagpure | DOB website updation | Designed 3 new SEO-friendly pages for the Digital One Box website in Figma based on the provided content. Improved the alignment and layout of existing website pages using CSS, updated images in the latest Figma designs, and ensured all pages followed the company's design guidelines. Finally, cross-verified the designs and UI updates to maintain consistency, responsiveness, and overall website quality. | NO | -- | PENDING | -- | -- | 22 Jul 2026, 06:55 pm | --
Anshul Tiwari | 2026-07-22 | Yogesh Rangade | ORAXEL | ORAXEL - logo design | -- | -- | PENDING | -- | -- | 22 Jul 2026, 12:29 pm | --
Swati Rinayat | 2026-07-23 | Sakshi Kawre | Exchange Token PPT | Completed content creation and refinement for the Exchange & Token Listing presentation, covering the company overview, project overview, core listing capabilities, and technology stack with structured, business-focused, and investor-ready content. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 06:24 pm | --
Dhurv Shukla | 2026-07-23 | Eiksha Upwanshi | CLIENT FOLLOW UPS CALLS | Daily Calls and Meeting Format Date - 23/07/2026 - Thursday 1. New Call – 00. 2. Old Database Call- 00. 3. Follow Call –31. 4. Total Calls –31. Qualified Calls – 00. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 05:48 pm | --
Shailesh Nagpure | 2026-07-23 | Yogesh Rangade | multiple | web3listing.com - all dns record add , free mail setup MM Bot - bifinance compatible bot creationtion , working on trade , chart , volume part cryptologus - admin , user, backend code upload on server MLLF -code upload on server Genvualt - code upload on server | -- | -- | PENDING | -- | -- | 27 Jul 2026, 12:25 pm | --
Soham Kavde | 2026-07-23 | Shailesh Nagpure | smartudhar | subscription plan, flow develop meetings | -- | -- | PENDING | -- | -- | 24 Jul 2026, 11:12 am | --
Sakshi Kawre | 2026-07-23 | Eiksha Upwanshi | Smart Udhar | Started working on the FINZO EX project, reviewing requirements and initiating the UI design process. Attended a project discussion with Mayank Sir to review requirements, design strategy, and project planning. Started redesigning the SmartUdhar Landing Page, focusing on layout improvements, visual hierarchy, and enhanced user experience. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 11:05 am | --
Shubham Thakre | 2026-07-23 | Shailesh Nagpure | CRM project | started working on project management. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 10:53 am | --
Ashvin Bisen | 2026-07-23 | Shailesh Nagpure | MLLF & DOB | MLLF Website All Pages Link Update & privacy policy & Term & Condition Page Update & Presale page Only Buy With USDT & tostify Popup Added Done. Digital One box Website "How to Choose the Right Blockchain Development Company in 2026" 1blog post Create done. & Digital one Box Website upload in Server Done. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 10:36 am | --
Sirish Diyawar | 2026-07-23 | Eiksha Upwanshi | Daily Tasks Report | 23-07-2026 crypto logus Social media post creation and posting 23-07-2026 digital one box blox content review 23-07-2026 samrtudhar post creation and posting 23-07-2026 Working on Whatsapp Automation frontend 23-07-2026 Meeting For smart udhar marketing | -- | -- | PENDING | -- | -- | 24 Jul 2026, 10:25 am | --
Aryant Shrirang | 2026-07-23 | Eiksha Upwanshi | Equinix AI + cryptora + DOB | Equinix ai ROI logic change as client wants roi should be lifetime for users for each investment , any investments roi should be given to user for that investments 30 day period , crypto logus , dynamic social media addition at admin side , for user , create read update delete api creation , letest build deployeed for Digital one box website , meeting with garima maam for the AI project , in 1st half and 2nd half 1 hr | meeting with garima maam for the AI project , | -- | PENDING | -- | -- | 24 Jul 2026, 10:23 am | --
Amrita Mishra | 2026-07-23 | Sirish Diyawar | All Project | 23-07-2026 * CIPERA BLOG AND IMAGE CONTENT CREATION, BLOG POSTING ON MEDIUM AND BLOG LINK POSTING ON ALL SOCIAL MEDIA PLATFORMS. * CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * ELITE X MINING CONTENT AND GRAPHIC CREATION AND POSTING * PROMPT LEARNING FOR RUNNING ADS THROUGH CLOUDE. * 3 MODULES APPLY ON CAMPAIGN- MODULE 1- CONNECTOR BASICS,MODULE 2- WRITING A PROMPT THROUGH CLOUDE, MODULE 3- CAMPAIGN CREATION + AUTOMATION. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 10:23 am | --
Akshay Daharwal | 2026-07-23 | Yogesh Rangade | FinzoEx Backend , EquinixAI and CRM | * Performed comprehensive FinzoEX backend API testing and resolved testing issues. * Deployed the CRM Frontend to the live server. * Deployed the CRM Backend to the live server. * Deployed the Equinix AI Frontend to the live server. * Deployed the Equinix AI Backend to the live server. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 07:03 pm | --
Nitu Bisen | 2026-07-23 | Shailesh Nagpure | Mllf-web | oday, I continued working on the MLLF Web project, focusing on improving the user interface and responsiveness of the website. Tasks Completed Updated and standardized the fonts across the Home, FAQ, and Tokenomics pages to ensure a consistent visual design. Added and integrated the required images and assets according to the Figma design. Improved the Home page by refining layouts, spacing, and overall responsiveness. Enhanced the FAQ section, making it fully responsive and ensuring proper alignment across different screen sizes. Worked on the Tokenomics page, updating the design, integrating images, and optimizing the responsive layout. Fixed styling inconsistencies and adjusted spacing, typography, and component alignment for a better user experience. | -- | -- | REVIEWED | Shubham Thakre | -- | 23 Jul 2026, 06:51 pm | 27 Jul 2026, 10:51 am
Sampann Tiwari | 2026-07-23 | Eiksha Upwanshi | FinzoEx | FinzoEx Home page development Continued developing the next sections Market place section developed Design fixed according to figma Responsive design checked Fixed responsive issues Quick Cards section developed Design matching as per the figma | System unreponsive Laptop issues | -- | PENDING | -- | -- | 23 Jul 2026, 06:50 pm | --
Sanjay Lilhare | 2026-07-23 | Eiksha Upwanshi | Digital One Box | Pending Payment Remainder Daily Balance sheet Update Project management sheet Update Market visit Bank Visit For Od account MMSKY Meeting New Office Contratction Work Process Camping Payment | -- | -- | PENDING | -- | -- | 23 Jul 2026, 06:43 pm | --
Nukul Lilhare | 2026-07-23 | Shailesh Nagpure | Figma of Dob | Worked in Figma on new page layouts and design concepts. Explored animation ideas to enhance user interaction and visual appeal. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 06:41 pm | --
Pankaj Nagpure | 2026-07-23 | Shailesh Nagpure | DOB website updation | Today, I designed and added new website pages in Figma based on the project requirements. I also reviewed and finalized the previously modified pages, implemented the required updates, and successfully built and deployed the latest version of the website, ensuring all changes were live and functioning correctly. | NO | -- | REVIEWED | Shubham Thakre | -- | 23 Jul 2026, 06:41 pm | 27 Jul 2026, 10:52 am
Shivam Patle | 2026-07-23 | Eiksha Upwanshi | Smart Udhar | Reviewed the Smart Udhar application and verified the latest implementation. Performed regression testing to ensure previously implemented features were working correctly. Monitored the production deployment and validated application stability. Reviewed reported issues and analyzed potential improvements for upcoming tasks. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 06:37 pm | --
Gouri Shankar | 2026-07-23 | Eiksha Upwanshi | Office CRM Project Module | 23-05-2026: Office CRM Backend Deadline Change Api Done , After project create mgr will define area ex: Create Area for Ui , Create Area for frontend ,For Backend For Blockchain Done’ While creating are Assgin to TL , upload required document , list of all area , Update Area api Done . In area mgr can give start date , estimated end date .this part done with specific area wise document collection . | -- | -- | PENDING | -- | -- | 23 Jul 2026, 06:16 pm | --
Amaan Khan | 2026-07-23 | Sirish Diyawar | Digital one Box & Smart Udhaar | 1. Digital One Box – Blog Creation Created a new blog for the Digital One Box website. Conducted keyword research and topic research to support SEO and content strategy. 2. 6-Month Content Strategy Developed a 6-month blog content plan for the Digital One Box blog. Planned a new service page launching strategy aligned with the content calendar. 3. Google Search Console Optimization Tested Digital One Box website URLs in Google Search Console. Identified unindexed pages and submitted them for reindexing to improve search visibility. 4. Project Meeting Attended a meeting with Sirish Sir regarding the SmartUdhaar project. 5. SmartUdhaar Research Conducted research on the SmartUdhaar project. Explored and documented the core concepts and key functionalities of the platform. | -- | -- | PENDING | -- | -- | 23 Jul 2026, 06:09 pm | --
Priyank Khairwar | 2026-07-23 | Eiksha Upwanshi | ORAXEL | Landing page create | -- | -- | PENDING | -- | -- | 23 Jul 2026, 11:26 am | --
Sirish Diyawar | 2026-07-23 | Eiksha Upwanshi | Daily Work Details | 22-07-2026 Crypto Logus Blog Posting 22-07-2026 interview of data analyst 22-07-2026 Working on Whatsapp Automation frontend 22-07-2026 samrt udhar Meeting with soham | -- | -- | PENDING | -- | -- | 23 Jul 2026, 10:26 am | --
Sakshi Kawre | 2026-07-24 | Eiksha Upwanshi | Smart Udhar Redesigning | Conducted research and redesigned the SmartUdhar Landing Page, focusing on competitor analysis, UI improvements, layout optimization, and enhanced user experience. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 01:42 pm | --
Anshul Tiwari | 2026-07-24 | Eiksha Upwanshi | All project task | EMPLOYEE OF THE - month post design Cipera - post design Cipera - meme - post design Silvernova - post design Silvernova - meme post design CrypGPT- post design oraxel - logo Symbol design cryptolugs - Animted GIF video | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:35 am | --
Swati Rinayat | 2026-07-24 | Sakshi Kawre | Exchange Token PPT | Completed listing workflow, exchange listing types (CEX, DEX & aggregators), platform UI/UX highlights, and admin panel capabilities. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 06:25 pm | --
Priyank Khairwar | 2026-07-24 | Eiksha Upwanshi | FINZO EX | FINZO EX OTC Desk Layout and wireframe . | -- | -- | PENDING | -- | -- | 27 Jul 2026, 06:22 pm | --
Dhurv Shukla | 2026-07-24 | Eiksha Upwanshi | follow up calls | Daily Calls and Meeting Format Date - 24/07/2026 - Friday 1. New Call – 00 2. Old Database Call- 16 3. Follow Call –8 4. Total Calls –24 Qualified Calls –00 | -- | -- | PENDING | -- | -- | 27 Jul 2026, 05:56 pm | --
Shubham Thakre | 2026-07-24 | Shailesh Nagpure | CRM Project | working on project management and fixed mobile version of crm website. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 05:53 pm | --
Shailesh Nagpure | 2026-07-24 | Yogesh Rangade | multiple | MM Bot - bifinance compatible bot creationtion , working on trade , chart , volume part ponsfamily.com - project completly check ( r&d part) , and functionality doc create https://aip.finance/ - mlm project check web3listing.com - nameserver and mail related dns update | -- | -- | PENDING | -- | -- | 27 Jul 2026, 12:26 pm | --
Ashvin Bisen | 2026-07-24 | Shailesh Nagpure | DOB & MLLF | Digital one Box Website Code Upload . MLLF Link Update & Homepage & Presale page Changes done. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 10:34 am | --
Aryant Shrirang | 2026-07-24 | Eiksha Upwanshi | Equinix ai + ai automation project | equinix ai production env problem , production issue , crones are not allowd from env , fixed ai automation project meeting with sirish sir and rakesh sir , DOB website monitoring , designes consistency + intern works | -- | -- | PENDING | -- | -- | 27 Jul 2026, 10:32 am | --
Gouri Shankar | 2026-07-24 | Eiksha Upwanshi | Office CRM | 24-07-2026: 1. Office CRM project module working on Backend with comment and activity log 2. Also implementing Crm frontend integration part . | -- | -- | PENDING | -- | -- | 27 Jul 2026, 10:30 am | --
Soham Kavde | 2026-07-24 | Shailesh Nagpure | smartudhar | 24-07-2026 Bug fix backend services | -- | -- | PENDING | -- | -- | 27 Jul 2026, 10:30 am | --
Amrita Mishra | 2026-07-24 | Sirish Diyawar | All Porject | 24-07-2026 * CIPERA SOCIAL MEDIA CONTENT CREATION AND POSTING. * CRYPGPT SOCIAL MEDIA CONTENT CREATION AND REEL CREATION AND POSTING. * SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND REEL CREATION AND POSTING. * ELITE X MINING CONTENT AND GRAPHIC CREATION AND POSTING * SOCIAL MEDIA ENGAGEMENT BUDGET CREATION FOR SILVERNOVA. * 3RD CAMPAIGN CREATION, RESEARCH ON NEW AUDIENCE AND LOCATION, AND CAMPAIGN SETUP. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 10:23 am | --
Atharv Churhe | 2026-07-24 | Shailesh Nagpure | Learning blockchain | Learning Blockchain | -- | -- | PENDING | -- | -- | 24 Jul 2026, 07:02 pm | --
Akshay Daharwal | 2026-07-24 | Eiksha Upwanshi | CRM, Equinix and Finzoex | * Deployed the CRM Frontend to the live server. * Deployed the CRM Backend to the live server. * Deployed the Equinix AI Frontend to the live server. * Deployed the Equinix AI Backend to the live server. * Performed comprehensive FinzoEX backend API testing and resolved testing issues. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 07:02 pm | --
Sampann Tiwari | 2026-07-24 | Eiksha Upwanshi | FinzoEX | FinzoEX Home page development completed Developed the remaining sections Trade section created Design and layout matched to figma Responsive design fixed CTA section created Footer created Made the design and layout match figma Responsive layouts checked Added animations to the components Vercel link created | System issues | -- | PENDING | -- | -- | 24 Jul 2026, 07:00 pm | --
Sirish Diyawar | 2026-07-24 | Eiksha Upwanshi | Daily Work Tasks | 24-07-2026 crypto logus Social media post creation and posting 24-07-2026 digital one box blog posting 24-07-2026 Working on Whatsapp Automation frontend 24-07-2026 Meeting For DOB Sale Workflow Loop 24-07-2026 marketing team review | -- | -- | PENDING | -- | -- | 24 Jul 2026, 06:57 pm | --
Shivam Patle | 2026-07-24 | Eiksha Upwanshi | FIXFITNESS APP | Worked on the Nutrition module in the FixFitness application. Implemented the functionality that allows users to generate personalized diet plans based on their preferences and fitness goals. Developed the diet tracking feature, enabling users to monitor their daily nutrition and diet progress. Integrated and validated the nutrition workflow to ensure accurate diet plan generation and tracking. Performed testing and bug fixes to ensure the Nutrition module was functioning smoothly. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 06:49 pm | --
Nitu Bisen | 2026-07-24 | Yogesh Rangade | Mllf-web | Today, I continued working on the MLLF Web project with a focus on developing new sections and improving the overall responsiveness of the website. Tasks Completed: Developed two new sections on the Home page based on the provided design. Made all website pages fully responsive for mobile, tablet, laptop, and desktop screen sizes. Improved the alignment and spacing across multiple pages to ensure a consistent and polished user interface. Adjusted layouts, typography, images, and component positioning for better responsiveness and visual consistency. Performed UI refinements to enhance the overall user experience and maintain pixel-perfect alignment with the design. | -- | -- | PENDING | -- | -- | 24 Jul 2026, 06:49 pm | --
Pankaj Nagpure | 2026-07-24 | Shailesh Nagpure | figma of DOB website | Today, I designed and added 3 new website pages in Figma based on the project requirements. I also updated new images in the website cards to enhance the visual appearance and ensure consistency with the overall design system. | NO | -- | REVIEWED | Shubham Thakre | -- | 24 Jul 2026, 06:49 pm | 27 Jul 2026, 10:48 am
Nukul Lilhare | 2026-07-24 | Shailesh Nagpure | Dob figma new pages design | Today i make 3 figma design pages . | -- | -- | PENDING | -- | -- | 24 Jul 2026, 06:45 pm | --
Amaan Khan | 2026-07-24 | Sirish Diyawar | DOB & Smartudhar | 1. Test Live URL's and submitting for Reindexing https://digitalonebox.com/ido-service https://digitalonebox.com/exchange-development https://digitalonebox.com/solana-blockchain-development https://digitalonebox.com/custom-crypto-solution https://digitalonebox.com/wallet-development https://digitalonebox.com/nft-service https://digitalonebox.com/web3-marketing 2. Webpage Digital one Box research -: Content Research Keyword research and mapping Creating FAQ's For the pages 4AEO and GEO Optimization for pages 3. New Webpages content Created :- NFT Staking Platform Development NFT Exchange Development NFT Marketplace White Label DeFi Development Staking Platform Development Cross-chain DeFi AMM Development Liquidity Pool Development 4. Smartudhar Project :- Documet the Unique Features Of Smartudhaar Application App testing | -- | -- | PENDING | -- | -- | 24 Jul 2026, 05:49 pm | --
Anshul Tiwari | 2026-07-24 | Amrita Mishra | daily task | Cipera - blog banner design cipera - post design Silvernova - post design CrypGPT- post design DOB- reel design & final editing | -- | -- | PENDING | -- | -- | 24 Jul 2026, 10:20 am | --
Amrita Mishra | 2026-07-25 | Sirish Diyawar | 25-07-2026 | * SILVERNOVA CAPTION CREATION AND POSTING ON ALL SOCIAL MEDIA PLATFORMS. * CRYPGPT CAPTION CREATION AND POSTING ON ALL SOCIAL MEDIA PLATFORMS. * CIPERA CAPTION CREATION AND POSTING ON ALL SOCIAL MEDIA PLATFORMS. * ELITE X MINING CAPTION CREATION AND POSTING. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 10:25 am | --
Sirish Diyawar | 2026-07-27 | Eiksha Upwanshi | Daily Task | 27-07-2026 crypto logus Social media post creation and posting 27-07-2026 digital one box blog posting 27-07-2026 Working on Whatsapp Automation frontend 27-07-2026 Meeting For Smart udhar 27-07-2026 Team Work Review 27-07-2026 Working ON social media report | -- | -- | PENDING | -- | -- | 28 Jul 2026, 06:58 pm | --
Sanjay Lilhare | 2026-07-27 | Eiksha Upwanshi | Digital One box pvt ltd | Account Meeting expense and emergency backup Pending Payment Remainder Office employee salary slip Create Daily Balance sheet Update Project management sheet Update | -- | -- | PENDING | -- | -- | 28 Jul 2026, 06:51 pm | --
Sakshi Kawre | 2026-07-27 | Eiksha Upwanshi | Smart Udhar Redesigning | Half Day : Worked on the SmartUdhar Landing Page redesign (half day), focusing on layout refinements, UI enhancements, and improving the overall user experience. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 01:45 pm | --
Akshay Daharwal | 2026-07-27 | Eiksha Upwanshi | EiteX , FinzoEx And CRM | * Implemented $10 Registration Fee ON/OFF functionality on the Elite X Admin Panel. * Developed the $10 Registration Fee feature in both(User and Admin) the Frontend and Backend. * Integrated and tested the complete $10 Registration Fee workflow across the application. * Deployed the CRM Frontend to the live server. * Deployed the CRM Backend to the live server. * Performed comprehensive FinzoEX backend API testing and resolved testing issues. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 11:47 am | --
Abhay Lilhare | 2026-07-27 | Eiksha Upwanshi | web3 listing | 1. Create a marketing strategy. 2. meeting with Mayank, sir 3. create web3 service content and add a website. 4. Runi token trade part management 5. Create a CMC profile in cmc and apply to verify | -- | -- | PENDING | -- | -- | 28 Jul 2026, 11:06 am | --
Shivam Patle | 2026-07-27 | Eiksha Upwanshi | FIXFITNESS APP | Implemented and enhanced the Continue with Google authentication flow in the FixFitness application. Improved the authentication process by resolving issues related to session refresh and token handling for a smoother user experience. Optimized the login and authentication workflow to improve application stability and performance. Performed code optimization and refactoring across multiple modules to enhance maintainability and responsiveness. Addressed minor UI and functionality improvements identified during testing. Conducted end-to-end testing to verify the Google Sign-In flow, refresh functionality, and overall application stability after the changes. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:50 am | --
Aryant Shrirang | 2026-07-27 | Eiksha Upwanshi | Equinix AI + dob website + AI project | Equinix ai meeting , to solve confusion of client dob website design check , guided for code structure , Ai project research about video sdk for price reduction , AI bases superfone CRM meeting with superfone team , AI calling agent , website enhancement , | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:43 am | --
Ashvin Bisen | 2026-07-27 | Shailesh Nagpure | Finzoex Exchnage | Finzoex Exchange OTC & margin trading part how to work & Project Workflow Create done. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:40 am | --
Gouri Shankar | 2026-07-27 | Eiksha Upwanshi | Office CRM Backend | 1. Crm project module working on backend with edit project api delete project api change status with planning , active , hold,under review , completed , archived , and cancled api. 2. Integrating frontend for project module . 3. Add multiple document , remove document on role basis api done on workarea for attachment 4. Project overall activity log file generation to track project status . | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:38 am | --
Soham Kavde | 2026-07-27 | Shailesh Nagpure | smartudhar | Bug fix, meeting with marketing team razorpay integrated | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:36 am | --
Shubham Thakre | 2026-07-27 | Shailesh Nagpure | CRM Project | creating task submission module and fixing minor bugs in CRM | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:32 am | --
Anshul Tiwari | 2026-07-27 | Eiksha Upwanshi | All project Task | Silvernova- post design Cipera - post design CrypGPT- post design dob -hiriing post design DOB- long reel design | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:31 am | --
Amrita Mishra | 2026-07-27 | Sirish Diyawar | 27-07-2026 | * CIPERA SOCIAL MEDIA CONTENT AND REEL CREATION. * CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * ELITE X MINING ONE WEEK CONTENT CREATION AND ALSO GRAPHIC CREATION AND POSTING. * DOB CAMPAIGN NEW FOR CREATION, CHANGES IN FORM CONTENT. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 10:28 am | --
Nitu Bisen | 2026-07-27 | Shailesh Nagpure | mllf-web | Today, I completed the MLLF Web project by finalizing all remaining tasks. I corrected UI alignment issues across multiple sections and ensured that every page is fully responsive for desktop, tablet, and mobile devices. I also performed final testing and made minor adjustments to improve the overall layout, consistency, and user experience. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 08:46 pm | --
Nukul Lilhare | 2026-07-27 | Shailesh Nagpure | Correction , reviewing | Today we work on correction of figma for taking next step to start building development from tomorrow. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 08:26 pm | --
Amaan Khan | 2026-07-27 | Sirish Diyawar | Smartudhar & Cryptologus | 1. Conducted research for the SmartUdhar project, including: Identified target customer segments. Analyzed customer adoption levels. Categorized customers based on priority for marketing and outreach. 2. Attended and participated in a team meeting to discuss the marketing strategy and promotional plans for the SmartUdhar project. 3. Performed keyword and topic research for the Cryptologus blog to identify relevant SEO opportunities and content ideas. 4. Wrote and finalized the Cryptologus blog article. 5. Created visuals for the Cryptologus blog and optimized images with Image SEO (file names, alt text, and other optimization practices). 6. Planned the category structure and subheading hierarchy for new add-on pages for the DOB website to improve content organization and scalability. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 08:06 pm | --
Dhurv Shukla | 2026-07-27 | Eiksha Upwanshi | old data based callinng | Daily Calls and Meeting Format Date - 27/07/2026 - Monday 1. New Call – 02. 2. Old Database Call- 08. 3. Follow Call – 37. 4. Total Calls –45. Qualified Calls – 00. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 07:00 pm | --
Atharv Churhe | 2026-07-27 | Shailesh Nagpure | Research on DeFiLlama | Research on DeFiLlama | -- | -- | PENDING | -- | -- | 27 Jul 2026, 06:57 pm | --
Pankaj Nagpure | 2026-07-27 | Shailesh Nagpure | DOB website pages Updation | Today, I started the frontend development of the Figma-designed website pages by converting the approved designs into responsive web layouts. | NO | -- | PENDING | -- | -- | 27 Jul 2026, 06:55 pm | --
Sampann Tiwari | 2026-07-27 | Eiksha Upwanshi | FinzoEX | FinzoEX Auth pages development started Created the app routes Public routes and auth routes created Auth layout created Developed the login page Applied fixes to the login page design | -- | -- | PENDING | -- | -- | 27 Jul 2026, 06:51 pm | --
Swati Rinayat | 2026-07-27 | Sakshi Kawre | FINZO EX | Today i hold PPT due to urgency of Finzo Ex ui screens. i designed OTC Desk UI screen including quote, desk highlightes, prices, overview and activity. one more P2P UI Screen | -- | -- | PENDING | -- | -- | 27 Jul 2026, 06:30 pm | --
Priyank Khairwar | 2026-07-27 | Eiksha Upwanshi | ORAXEL | The client has requested changes to the entire design layout and overall design. | -- | -- | PENDING | -- | -- | 27 Jul 2026, 06:26 pm | --
Abhay Lilhare | 2026-07-28 | Eiksha Upwanshi | web3 listing | Meeting with Mayank, sir runi trade part management Web3 marketing content ready | -- | -- | PENDING | -- | -- | 29 Jul 2026, 12:22 pm | --
Sakshi Kawre | 2026-07-28 | Eiksha Upwanshi | smartudhar landing page redesign | Continued the SmartUdhar Landing Page redesign, improving visuals, content layout, and overall usability. | -- | -- | PENDING | -- | -- | 29 Jul 2026, 12:05 pm | --
Soham Kavde | 2026-07-28 | Eiksha Upwanshi | smartudhar | 3 year plan added both admin and user side design changed | I still have not recieve the payment flow and user behaviour with subscription modal. | -- | PENDING | -- | -- | 29 Jul 2026, 11:35 am | --
Shubham Thakre | 2026-07-28 | Shailesh Nagpure | CRM Project | Working on project management module. | -- | -- | PENDING | -- | -- | 29 Jul 2026, 11:31 am | --
Aryant Shrirang | 2026-07-28 | Eiksha Upwanshi | AI agent calling + dob website | dob website new navigation creation for batter view and incomming pages ai calling new agent creation , for batter user experience , ( asha named femail agent ) | -- | -- | PENDING | -- | -- | 29 Jul 2026, 11:08 am | --
Shivam Patle | 2026-07-28 | Eiksha Upwanshi | SmartUdhar | Worked on the Smart Udhar deep linking feature. Researched how to open the app directly from WhatsApp daily reminder notifications. Implemented the deep link flow for opening the app from the notification link. Tested the deep link on different devices and checked the app opening behavior. Fixed issues found during testing and improved the deep linking flow. Verified that the feature was working as expected after the changes. | -- | -- | PENDING | -- | -- | 29 Jul 2026, 11:02 am | --
Amrita Mishra | 2026-07-28 | Sirish Diyawar | All Project | * CIPERA SOCIAL MEDIA CONTENT CREATION AND POSTING. * CRYPGPT SOCIAL MEDIA CONTENT CREATION AND POSTING. * SILVERNOVA SOCIAL MEDIA CONTENT CREATION AND POSTING. * ELITE X MINING ONE WEEK CONTENT CREATION AND ALSO GRAPHIC CREATION AND POSTING. * CAMPAIGN ONE WEEK REPORT CREATION. * CRYPGPT TWO WEEKS SOCIAL MEDIA REPORT CREATION. * DHURUV CAMPAIGN DATA ADD-ON CAMPAIGN DOC. * MARKETING MEETING WITH MAYANK SIR | -- | -- | PENDING | -- | -- | 29 Jul 2026, 10:56 am | --
Gouri Shankar | 2026-07-28 | Eiksha Upwanshi | Office CRM | 28-07-2026: 1. Office CRM project module on backend , Create work area , get work area , upload multiple documents on work area , remove documents api done 2. Work area update api , Assign work area to team lead , Add project lead , list of all document get api , delete document api , delete work area api done 3. Work area forntendend new pages developed and integration on whole page . 4. Planning for next phase with resolving old bugs | -- | -- | PENDING | -- | -- | 29 Jul 2026, 10:39 am | --
Nitu Bisen | 2026-07-28 | Yogesh Rangade | mllf-web | Today, I worked on the MLLF web project. I improved the responsiveness across different screen sizes, ensuring the layout adapts smoothly on mobile, tablet, and desktop devices. I also reduced unnecessary spacing and gaps between sections and components to create a cleaner, more balanced, and visually consistent user interface while preserving the desktop design. | -- | -- | PENDING | -- | -- | 29 Jul 2026, 10:16 am | --
Nukul Lilhare | 2026-07-28 | Eiksha Upwanshi | Development ,figma | Today we fix figma under guidance of Amman sir and understand project for development by Aryant sir then started section of custom pages. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 09:12 pm | --
Pankaj Nagpure | 2026-07-28 | Eiksha Upwanshi | Development_DOB web-Pages | Developed one new Figma-designed page in React for the Digital One Box website and made necessary design corrections in Figma. | NO | -- | PENDING | -- | -- | 28 Jul 2026, 08:37 pm | --
Akshay Daharwal | 2026-07-28 | Yogesh Rangade | FinzoEx | * Converted parts of the Finzo Ex project from CommonJS to ES6 Modules. * Performed extensive API testing for the Finzo Ex project and identified/tested multiple endpoints. | -- | -- | PENDING | -- | -- | 28 Jul 2026, 07:07 pm | --
Amaan Khan | 2026-07-28 | Sirish Diyawar | Digital One Box SEO | "1. Conducted topic research for the blog. 2. Performed keyword research and finalized the target keywords. 3. Wrote and finalized the blog content for Digital One Box. 4. Created visual images for the blog and optimized them with image SEO best practices. 5. Verified whether the pages submitted for reindexing have been successfully indexed. 6. Identified gaps and issues preventing certain pages from being indexed. 7. Created new FAQ pages using React.js." | -- | -- | PENDING | -- | -- | 28 Jul 2026, 07:01 pm | --
Sirish Diyawar | 2026-07-28 | Eiksha Upwanshi | Daily Tasks | 28-07-2026 Working on Whatsapp Automation frontend 28-07-2026 Create Overall social media final Report 28-07-2026 Create What we sell & Outreach Document 28-07-2026 Interview OF Video Editor 28-07-2026 Social media Posting OF DOB | -- | -- | PENDING | -- | -- | 28 Jul 2026, 06:58 pm | --
Sampann Tiwari | 2026-07-28 | Eiksha Upwanshi | FinzoEX | FinzoEX Auth pages development complete Created the login and signup page Full design matched according to figma responsive layout checked Created the dashboard layout Dashboard route created Sidebar developed and matched the design with figma | -- | -- | PENDING | -- | -- | 28 Jul 2026, 06:57 pm | --
Sanjay Lilhare | 2026-07-28 | Eiksha Upwanshi | Digital one box pvt ltd | Account Meeting expense and emergency backup Pending Payment Remainder Office employee salary slip Create Daily Balance sheet Update Project management sheet Update Electricity bill optomize | -- | -- | PENDING | -- | -- | 28 Jul 2026, 06:51 pm | --
Priyank Khairwar | 2026-07-28 | Eiksha Upwanshi | ORAXEL | The client has requested changes to the entire design layout and overall design. Completed {Submit} | -- | -- | PENDING | -- | -- | 28 Jul 2026, 11:17 am | --